How are we performing?

Integrated Performance Report

Quarter 2 (July to September 2008)

For further information or copies of this report, contact the People and Policy Team: Lee Birkett Tel: 01706 252454, e-mail: leebirkett@rossendalebc.gov.uk.

The Council’s Corporate Plan is available from the People and Policy Team or to download from:  http://www.rossendale.gov.uk/downloads/rbc_corporate_plan_final_-_low_res.pdf.

How are we performing?

The Council’s Corporate Plan for 2008–11 sets out the Council’s six priority themes which represent the main aims of Rossendale Borough Council. Against each of these priorities we have set out a range of actions, measures and targets for achievement. This report will tell you how well we are doing in delivering our priorities by; demonstrating the progress we are achieving in completing the actions and targets in our corporate plan together with providing key performance management information about the Council’s performance.

Section 1 – High level performance summary

Section 2 – Our Performance by Priority

The report is supported by more detailed statistical information on the achievement of targets and descriptive commentary on current levels of performance, as follows:

Section 3 – Corporate Plan Actions, Covalent Report

Section 4 – Performance Indicators, Covalent Report

Section 5 – Risks, Covalent Report

Section 6 – Financial Health Indicators

Section 7 – Complaints

Data Quality

Rossendale Council is committed to improving services for local people; we recognise that strong performance management and robust data quality processes are an important part of helping us achieve this. Data Quality is about making sure that the data and information we use to compile this report is accurate, reliable and is provided in a timely manner. The council has introduced a Performance Management & Data Quality Strategy to ensure that all performance information (including the information you find in this document) continues to be collected and used efficiently and effectively to drive improvements in our services.

Who supplied the performance data for this report?

The People & Policy team recognises that this report could not be produced without the timely, accurate and reliable contributions of officers throughout the Council. This report was compiled in October 2008 by the Council’s People & Policy Team using the latest performance information input onto the Covalent performance management system by officers with responsibility for performance information from each of the Council’s service areas. The data on complaints was provided by the Service Assurance Team and financial information by the Head of Financial Services.

Data Quality Issues

The Overview and Scrutiny Committee March 2008 considered the abolition of the Best Value Performance Indicators and the introduction of the new set of National Indicators. Thirty Five of the National Indicators are included within the Local Area Agreement.

Consultation is still ongoing in relation to the definitions and the methodology for collection of some of the National Indicators.  Furthermore, some performance data is not currently collated and consequently 2008/09 will be a year of benchmarking performance.  This is specifically in relation to criminal damage preventing extremism and reducing incidents of domestic violence.  Consultation is ongoing with Lancashire County Council and the Audit Commission.

It has been agreed that the BVPIs which continue to be collected will be recorded as Local Performance Indicators (LIs).

The following National Indicators are contained in the LAA35; lead officers are identified in relation to those indicators the District Council contributes to:

| Target Description | Lead Officer in the organisation or Partner | Lead or Contributing |
| --- | --- | --- |
| NI 186 - Per capita CO2 emissions in the LA area | Environmental Health Manager | Contributing |
| NI 188 - Adapting to climate change | Environmental Health Manager | Contributing |
| NI 195 - Improved street and environmental cleanliness (levels of graffiti, litter, detritus and fly posting | Neat Manager | Contributing |
| NI 155 - Number of affordable homes delivered (gross) | Head of Regeneration | Lead |
| NI 192 - Household waste recycled and composted | Street scene manager | Contributing |
| NI 197 - Improved local biodiversity – active management of local sites | Environmental Health Manager | Contributing |
| NI 187 - Tackling Fuel Poverty | Head of Regeneration | Contributing |
| NI 153 - Working age people claiming out of work benefits in the worst performing neighbourhoods | Head of Regeneration | Contributing |
| NI 163 - Working age population qualified to at least Level 2 or higher | Head of Regeneration | Contributing |
| NI 165 - Working age population qualified to at least Level 4 or higher | Head of Regeneration |  |
| NI 166 - Average earnings of employees in the area | Head of Regeneration | Contributing |
| NI 171 - New business registration rate | Head of Regeneration | Contributing |
| NI 137 - Healthy life expectancy at age 65 | East Lancashire PCT | Contributing |
| NI 139 - People over 65 who say that they receive the information, assistance and support needed to exercise choice and control to live independently | East Lancashire PCT | Not Contributing |
| NI 142 - Number of vulnerable people who are supported to maintain independent living | Head of Regeneration | Contributing |
| NI 39 - Alcohol-harm related hospital admission rates | East Lancashire PCT | Contributing |
| NI 119 - Self-reported measure of people’s overall health and wellbeing | East Lancashire PCT | Contributing |
| NI 120 - All-age all cause mortality rate | East Lancashire PCT | Contributing |
| NI 123 - 16+ current smoking rate prevalence (number of 4-week quitters) | East Lancashire PCT | Contributing |
| NI 124 - People with a long-term condition supported to be independent and in control of their condition | East Lancashire PCT | Not Contributing |
| NI 50 - Emotional Health of Children | Children’s Trust | Contributing |
| NI 55 - Obesity among primary school age children in Reception Year (Percentage of children recorded as being obese) | Children’s Trust | Contributing |
| NI 110 - Young people’s participation in positive activities | Children’s Trust | Contributing |
| NI 112 - Under 18 conception rate | East Lancashire PCT | Contributing |
| NI 117 - 16 - 18 year olds who are not in education, training or employment (NEET) | Children’s Trust | Contributing |
| NI 16 - Serious Acquisitive Crime Rate | Community Safety Manager | Contributing |
| NI 30 - Re-offending rate of prolific and priority offenders | Community Safety Manager | Contributing |
| NI 40 - Drug users in effective treatment. | Community Safety Manager | Contributing |
| NI 47 - People killed or seriously injured in road traffic accidents | Community Safety Manager | Contributing |
| NI 49 - Number of primary fires and related fatalities and non-fatal casualties, excluding precautionary checks | Community Safety Manager | Contributing |
| NI 20 - Assault with injury crime rate | Community Safety Manager | Contributing |
| NI 1 - People from different backgrounds getting on well together | Communities Manager | Contributing |
| NI 4 - % of people who feel they can influence decisions in their locality | Communities Manager | Contributing |
| NI 6 - Participation in regular volunteering | Communities Manager | Contributing |
| NI 7 - Environment for a thriving third sector | Communities Manager | Contributing |

Recommendations:

- That Performance Scrutiny reviews the performance achievement detailed within this report.

Section 1 – High level performance summary

This section of the report provides an overall summary of how the Council is performing against a range of key measures of performance.

1.1 Rossendale Council’s Corporate Plan – project implementation

The actions contained in the Corporate Plan represent the Council’s highest priority projects - the effective implementation of these projects is essential in achieving the Council’s stated priorities.  Each project is assigned to a ‘Portfolio Holder’, together with a ‘lead officer’ who is responsible for the effective completion of the target by the agreed due date. Progress up-dates are required against each action which is due for completion within a date that is within 3 months of the project completion date.

Are we achieving the actions set put in the Councils Corporate Plan?

| Corporate Plan Actions |  |  |  |
| --- | --- | --- | --- |
| Legend | Status | No. | % |
| Green | Project on track, no substantial issues or risks which require action from the Council’s Programme Board | 20 | 80% |
| Amber | Some issues or risks which require action from the Council’s Programme Board to keep the project on track | 5 | 20% |
| Red | Project in jeopardy – serious issues or risks needing urgent action | 0 | 0% |
|  | Total number of actions | 25 |  |

1.2 Performance Indicators – achieving targets?

Each year the Council sets targets for achievement against a range of performance indicators and regularly monitors throughout the year how well it is doing in achieving the targets it has set. The following table sets out how many targets are currently on track against National and Local Indicators, and against the targets that the Council is responsible for achieving contained in the Local Area Agreement for Lancashire.

| Legend |  | Status | LANCASHIRE LOCAL AREA AGREEMENT (LAA35) INDICATORS |  | OTHER NATIONAL INDICATORS |  | LOCAL INDICATORS |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | No. | % | No. | % | No. | % |
| On Target |  | The performance indicator has achieved or exceeded it’s quarter 3 target | 4 | 100% | 3 | 100% | 14 | 74% |
| Marginally Below Target |  | The performance indicator is currently 5% or less from achieving its target | 0 | 0% | 0 | 0% | 3 | 16% |
| Below Target |  | The performance indicator is currently more than 5% of achieving its target | 0 | 0% | 0 | 0% | 2 | 10% |
| Unknown |  | The status cannot be calculated | 0 | 0% | 0 | 0% | 0 | 0% |
| Contextual |  | Not measured against a target | 0 | 0% | 0 | 0% | 0 | 0% |
| Total for Quarter 2 |  |  | 4 |  | 3 |  | 19 |  |

1.3 How are we performing in managing our risks?

Are we reducing the Likelihood and Impact of our Risks?

| Risks |  |  |  |
| --- | --- | --- | --- |
| Legend | Status | No. | % |
| Green | The likelihood and impact of the risk is low | 44 | 54% |
| Amber | The likelihood and impact of the risk is medium | 26 | 32% |
| Red | The likelihood and impact of the risk is high | 11 | 14% |
|  | Total | 81 |  |

  - Reducing the Risks faced by the Council

Risks are those things which might present a barrier to us delivering the things we have undertaken to achieve. Each year the Council considers and reviews the potential risks it is facing and looks at what it might do to minimise the occurrence of such risks – this information is then regularly monitored and reviewed.

We profile our risks using a standard matrix (shown below) which is based on our making two judgments about each potential risk faced by the Council

The Council’s Risk Matrix

| Likelihood | A |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | B |  |  |  |  |
|  | C |  |  |  |  |
|  | D |  |  |  |  |
|  | E |  |  |  |  |
|  | F |  |  |  |  |
|  |  | 4 | 3 | 2 | 1 |
|  | Impact |  |  |  |  |

- How likely is it that the risk may occur (likelihood)?

- If the risk did occur, how serious might be the consequences (impact)?

(Therefore a risk rated A1 is the highest risk rating and a risk of F4 is the lowest rating.)

Section 2 – Performance against the Council’s Priorities

Each year the Council reviews and identifies its top priorities for achievement. The budget allocation and corporate and business planning processes are then used to direct the Council’s resources and efforts towards achieving its stated priorities. The following section of the report monitors the Council’s performance under each of the Council’s six priorities.

Priority 1 – Delivering quality services to our customers

The Council has committed to deliver a range of actions and projects that are specifically aimed at “Delivering Quality services to our customers”. We have also set ourselves a range of targets and deadlines to be achieved, and identified the ‘risks’ which are those things that might present a barrier to delivering the targets we have undertaken to achieve. This section of the report summarises how well we are performing in delivering this priority.

1.1	How are we performing in delivering quality services to our customers?

| Elements of performance that contribute towards the achievement of Priority 1 | Totals | GREEN |  | AMBER |  | RED |  | UNKNOWN |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Plan Actions | 7 | 7 | 100% | 0 | 0% | 0 | 0% | 0 | 0% |
| Lancashire Local Area Agreement (LAA35) Indicators | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |
| Other National Indicators | 2 | 2 | 100% | 0 | 0% | 0 | 0% | 0 | 0% |
| Local Indicators | 3 | 2 | 67% | 1 | 33% | 0 | 0% | 0 | 0% |
| Risks | 32 | 15 | 47% | 14 | 44% | 3 | 9% | 0 | 0% |
| Total | 44 | 26 | 59% | 15 | 34% | 3 | 7% | 0 | 0% |

1.2	Financial Monitoring

The following table analyses the various service area net financial resources across the priority area. In some instances a service area may not be directly involved in delivering a corporate priority and therefore the financial resources involved will be zero (for example Financial Services department resources are focused entirely on a “Well Managed Council” whereas Street Scene and Neighbourhood Services” are focused across a variety of customer facing Council priorities.

The table therefore identifies the service area, net annual budget expenditure, net forecast spend and therefore the total forecast variance for the year.

|  | Net Budget £000 | Net Forecast £000 | Variance £000 |
| --- | --- | --- | --- |
| By Service Area |  |  |  |
| Operational Services |  |  |  |
| Place Operations | 0 | 0 | 0 |
| Customer Services and e Government | 2,779 | 2,783 | (3) |
| Communities | 26 | 13 | 13 |
| Regeneration | 0 | 0 | 0 |
| Business |  |  |  |
| Building Control | 0 | 0 | 0 |
| Planning | 0 | 0 | 0 |
| Environmental Health | 0 | 0 | 0 |
| Legal & Democratic Services | 0 | 0 | 0 |
| Support Services |  |  |  |
| Finance & Property Services | 0 | 0 | 0 |
| Corporate Management | 0 | 0 | 0 |
| People and Policy | 0 | 0 | 0 |
| Non-Distributed Costs | 0 | 0 | 0 |
|  | 2,805 | 2,796 | 9 |

N.B. Figures are rounded up to the nearest whole number.

| Key variances |  |
| --- | --- |
| Recovery of Housing Benefit over payments | (36) |
| Staffing Vacancies | 20 |
| Court Cost - Council Tax Arrears | 17 |
| Markets Income | 13 |
| Software Licenses | 26 |
| Investment in Disaster Recovery | (15) |
| Saving on Outsourced IT Contract | (17) |
| Saving on outsourced revenues & benefits contract | 9 |
| Air Conditioning - IT Server Room | (5) |
| Miscellaneous | (3) |
|  | 9 |

Priority 2 – Delivering regeneration across the Borough

The Council has committed to deliver a range of actions and projects that are specifically aimed at “Delivering regeneration in Rossendale”. We have also set ourselves a range of targets and deadlines to be achieved, and identified the ‘risks’ which are those things that might present a barrier to delivering the targets we have undertaken to achieve. This section of the report summarises how well we are performing in delivering this priority.

2.1	How are we performing in delivering regeneration across the borough?

| Elements of performance that contribute towards the achievement of Priority 2 | Totals | GREEN |  | AMBER |  | RED |  | UNKNOWN |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Plan Actions | 10 | 6 | 60% | 4 | 40% | 0 | 0% | 0 | 0% |
| Lancashire Local Area Agreement (LAA35) Indicators | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |
| Other National Indicators | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |
| Local Indicators | 4 | 3 | 75% | 0 | 0% | 1 | 25% | 0 | 0% |
| Risks | 7 | 4 | 57% | 2 | 29% | 1 | 14% | 0 | 0% |
| Total | 21 | 13 | 62% | 6 | 29% | 2 | 9% | 0 | 0% |

2.2	Financial Monitoring

The following table analyses the various service area net financial resources across the priority area. In some instances a service area may not be directly involved in delivering a corporate priority and therefore the financial resources involved will be zero (for example Financial Services department resources are focused entirely on a “Well Managed Council” whereas Street Scene and Neighbourhood Services” are focused across a variety of customer facing Council priorities.

The table therefore identifies the service area, net annual budget expenditure, net forecast spend and therefore the total forecast variance for the year.

|  | Net Budget £000 | Net Forecast £000 | Variance £000 |
| --- | --- | --- | --- |
| By Service Area |  |  |  |
| Operational Services |  |  |  |
| Place Operations | 0 | 0 | 0 |
| Customer Services and e Government | 0 | 0 | 0 |
| Communities | 0 | 0 | 0 |
| Regeneration | 470 | 390 | 79 |
| Business |  |  |  |
| Building Control | 134 | 124 | 9 |
| Planning | 528 | 607 | (79) |
| Environmental Health | 0 | 0 | 0 |
| Legal & Democratic Services | 0 | 0 | 0 |
| Support Services |  |  |  |
| Finance & Property Services | 0 | 0 | 0 |
| Corporate Management | 0 | 0 | 0 |
| People and Policy | 0 | 0 | 0 |
| Non-Distributed Costs | 0 | 0 | 0 |
| (Variance in brackets denotes an overspend) | 1,132 | 1,122 | 10 |

N.B. Figures are rounded up to the nearest whole number.

| Key variances |  |
| --- | --- |
| Regeneration Staff Vacancies | 58 |
| Various Regeneration non pay budgets | 17 |
| Parking Income | 5 |
| Reduction in Land Charges Income | (60) |
| Planning - various non pay budgets | (10) |
|  | 10 |

Priority 3 – Keeping our Borough clean and green

The Council has committed to deliver a range of actions and projects that are specifically aimed at “Keeping our Borough clean and green”. We have also set ourselves a range of targets and deadlines to be achieved, and identified the ‘risks’ which are those things that might present a barrier to delivering the targets we have undertaken to achieve. This section of the report summarises how well we are performing in delivering this priority.

3.1	How are we performing in keeping our borough clean and green?

| Elements of performance that contribute towards the achievement of Priority 3 | Totals | GREEN |  | AMBER |  | RED |  | UNKNOWN |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Plan Actions | 2 | 1 | 50% | 1 | 50% | 0 | 0% | 0 | 0% |
| Lancashire Local Area Agreement (LAA35) Indicators | 1 | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% |
| Other National Indicators | 1 | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% |
| Local Indicators | 5 | 5 | 100% | 0 | 0% | 0 | 0% | 0 | 0% |
| Risks | 1 | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% |
| Total | 10 | 9 | 90% | 1 | 10% | 0 | 0% | 0 | 0% |

3.2	Financial Monitoring

The following table analyses the various service area net financial resources across the priority area. In some instances a service area may not be directly involved in delivering a corporate priority and therefore the financial resources involved will be zero (for example Financial Services department resources are focused entirely on a “Well Managed Council” whereas Street Scene and Neighbourhood Services” are focused across a variety of customer facing Council priorities.

The table therefore identifies the service area, net annual budget expenditure, net forecast spend and therefore the total forecast variance for the year.

| N.B. Figures are rounded up to the nearest whole number. | Net Budget £000 | Net Forecast £000 | Variance £000 |
| --- | --- | --- | --- |
| By Service Area |  |  |  |
| Operational Services |  |  |  |
| Place Operations | 3,864 | 3,814 | 50 |
| Customer Services and e Government | 0 | 0 | 0 |
| Communities | 423 | 383 | 40 |
| Regeneration | 0 | 0 | 0 |
| Business |  |  |  |
| Building Control | 0 | 0 | 0 |
| Planning | 0 | 0 | 0 |
| Environmental Health | 0 | 0 | 0 |
| Legal & Democratic Services | 0 | 0 | 0 |
| Support Services |  |  |  |
| Finance & Property Services | 0 | 0 | 0 |
| Corporate Management | 0 | 0 | 0 |
| People and Policy | 0 | 0 | 0 |
| Non-Distributed Costs | 0 | 0 | 0 |
|  | 4,287 | 4,197 | 90 |

| Key variances |  |
| --- | --- |
| Fuel for Refuse, Street Sweeping & Parks Vehicles | (46) |
| Cemeteries Income | 60 |
| Income from recycled paper | 27 |
| Onward transportation of Glass, Cans & Plastics | 28 |
| Publicity / Printing /Postage | (21) |
| Staffing / Agency Costs | 3 |
| Dog Warden Service | 8 |
| Area Team Staff Vacancies | 39 |
| Area Team Non Pay Budget | (8) |
|  | 90 |

Priority 4 – Promoting Rossendale as a cracking place to live and visit

The Council has committed to deliver a range of actions and projects that are specifically aimed at “Promoting Rossendale as a cracking place to live and visit”. We have also set ourselves a range of targets and deadlines to be achieved, and identified the ‘risks’ which are those things that might present a barrier to delivering the targets we have undertaken to achieve. This section of the report summarises how well we are performing in delivering this priority.

4.1	How are we performing in promoting Rossendale as a cracking place to live and visit?

| Elements of performance that contribute towards the achievement of Priority 4 | Totals | GREEN |  | AMBER |  | RED |  | UNKNOWN |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Plan Actions | 3 | 3 | 100% | 0 | 0% | 0 | 0% | 0 | 0% |
| Lancashire Local Area Agreement (LAA35) Indicators | 1 | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% |
| Other National Indicators | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |
| Local Indicators | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |
| Risks | 3 | 1 | 33% | 1 | 33% | 1 | 33% | 0 | 0% |
| Total | 7 | 5 | 71% | 1 | 14% | 1 | 14% | 0 | 0% |

4.2	Financial Monitoring

The following table analyses the various service area net financial resources across the priority area. In some instances a service area may not be directly involved in delivering a corporate priority and therefore the financial resources involved will be zero (for example Financial Services department resources are focused entirely on a “Well Managed Council” whereas Street Scene and Neighbourhood Services” are focused across a variety of customer facing Council priorities.

The table therefore identifies the service area, net annual budget expenditure, net forecast spend and therefore the total forecast variance for the year.

|  | Net Budget £000 | Net Forecast £000 | Variance £000 |
| --- | --- | --- | --- |
| By Service Area |  |  |  |
| Operational Services |  |  |  |
| Place Operations | 0 | 0 | 0 |
| Customer Services and e Government | 0 | 0 | 0 |
| Communities | 354 | 284 | 70 |
| Regeneration | 0 | 0 | 0 |
| Business |  |  |  |
| Building Control | 0 | 0 | 0 |
| Planning | 0 | 0 | 0 |
| Environmental Health | 0 | 0 | 0 |
| Legal & Democratic Services | 0 | 0 | 0 |
| Support Services |  |  |  |
| Finance & Property Services | 0 | 0 | 0 |
| Corporate Management | 0 | 0 | 0 |
| People and Policy | 157 | 157 | 0 |
| Non-Distributed Costs | 0 | 0 | 0 |
|  | 511 | 441 | 70 |

N.B. Figures are rounded up to the nearest whole number.

| Key variances |  |
| --- | --- |
| Income from Council Tax on 2nd Homes | 11 |
| Income generation | 16 |
| 4 x local Plans | (15) |
| Community Development Initiatives | (12) |
| Communities - Staff Vacancies | 10 |
| Communities - Consultancy budget | 10 |
| Local Strategic Partnership - 2nd Homes Income | 11 |
| Return of ELeP monies | 26 |
| Local Strategic Partnership - various non pay budgets | 13 |
|  | 70 |

Priority 5 – Improving health and well being across the Borough

The Council has committed to deliver a range of actions and projects that are specifically aimed at “Improving health and well being across the Borough”. We have also set ourselves a range of targets and deadlines to be achieved, and identified the ‘risks’ which are those things that might present a barrier to delivering the targets we have undertaken to achieve. This section of the report summarises how well we are performing in delivering this priority.

5.1	How are we performing in improving health and well being across the Borough?

| Elements of performance that contribute towards the achievement of Priority 5 | Totals | GREEN |  | AMBER |  | RED |  | UNKNOWN |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Plan Actions | 1 | 1 | 100% | 0 | 0% | 0 | 0% | 0 | 0% |
| Lancashire Local Area Agreement (LAA35) Indicators | 2 | 2 | 100% | 0 | 0% | 0 | 0% | 0 | 0% |
| Other National Indicators | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |
| Local Indicators | 1 | 0 | 0% | 0 | 0% | 1 | 100% | 0 | 0% |
| Risks | 5 | 3 | 60% | 1 | 20% | 1 | 20% | 0 | 0% |
| Total | 9 | 6 | 67% | 1 | 11% | 2 | 22% | 0 | 0% |

5.2	Financial Monitoring

The following table analyses the various service area net financial resources across the priority area. In some instances a service area may not be directly involved in delivering a corporate priority and therefore the financial resources involved will be zero (for example Financial Services department resources are focused entirely on a “Well Managed Council” whereas Street Scene and Neighbourhood Services” are focused across a variety of customer facing Council priorities.

The table therefore identifies the service area, net annual budget expenditure, net forecast spend and therefore the total forecast variance for the year.

|  | Net Budget £000 | Net Forecast £000 | Variance £000 |
| --- | --- | --- | --- |
| By Service Area |  |  |  |
| Operational Services |  |  |  |
| Place Operations | 0 | 0 | 0 |
| Customer Services and e Government | 0 | 0 | 0 |
| Communities | 438 | 432 | 6 |
| Regeneration | 183 | 191 | (8) |
| Business |  |  |  |
| Building Control | 0 | 0 | 0 |
| Planning | 0 | 0 | 0 |
| Environmental Health | 780 | 739 | 41 |
| Legal & Democratic Services | 0 | 0 | 0 |
| Support Services |  |  |  |
| Finance & Property Services | 0 | 0 | 0 |
| Corporate Management | 0 | 0 | 0 |
| People and Policy | 0 | 0 | 0 |
| Non-Distributed Costs | 0 | 0 | 0 |
|  | 1,401 | 1,362 | 39 |

N.B. Figures are rounded up to the nearest whole number.

| Key variances |  |
| --- | --- |
| Homelessness | (9) |
| Environmental Health - staff vacancies | 7 |
| Environmental Health - non pay budgets | 5 |
| Environmental - Misc (Public Burials etc) | 4 |
| Emergency Planning | 11 |
| Land Drainage - payments to Private Contractors | 10 |
| Licensing | 3 |
| Communities - various | 6 |
| Miscellaneous | 2 |
|  | 39 |

Priority 6 – A well managed Council

The Council has committed to deliver a range of actions and projects that are specifically aimed at maintaining “A well managed Council”. We have also set ourselves a range of targets and deadlines to be achieved, and identified the ‘risks’ which are those things that might present a barrier to delivering the targets we have undertaken to achieve. This section of the report summarises how well we are performing in delivering this priority.

6.1	How are we performing in maintaining a well managed Council?

| Elements of performance that contribute towards the achievement of Priority 6 | Totals | GREEN |  | AMBER |  | RED |  | UNKNOWN |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Plan Actions | 2 | 2 | 100% | 0 | 0% | 0 | 0% | 0 | 0% |
| Lancashire Local Area Agreement (LAA35) Indicators | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |
| Other National Indicators | 0 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% |
| Local Indicators | 6 | 4 | 67% | 2 | 33% | 0 | 0% | 0 | 0% |
| Risks | 34 | 20 | 59% | 8 | 23% | 5 | 15% | 1 | 3% |
| Total | 42 | 26 | 62% | 10 | 24% | 5 | 12% | 1 | 2% |

6.2	Financial Monitoring

The following table analyses the various service area net financial resources across the priority area. In some instances a service area may not be directly involved in delivering a corporate priority and therefore the financial resources involved will be zero (for example Financial Services department resources are focused entirely on a “Well Managed Council” whereas Street Scene and Neighbourhood Services” are focused across a variety of customer facing Council priorities.

The table therefore identifies the service area, net annual budget expenditure, net forecast spend and therefore the total forecast variance for the year.

| N.B. Figures are rounded up to the nearest whole number. | Net Budget £000 | Net Forecast £000 | Variance £000 |
| --- | --- | --- | --- |
| By Service Area |  |  |  |
| Operational Services |  |  |  |
| Place Operations | 0 | 0 | 0 |
| Customer Services and e Government | 0 | 0 | 0 |
| Communities | 0 | 0 | 0 |
| Regeneration | 0 | 0 | 0 |
| Business |  |  |  |
| Building Control | 0 | 0 | 0 |
| Planning | 0 | 0 | 0 |
| Environmental Health | 0 | 0 | 0 |
| Legal & Democratic Services | 1,131 | 1,077 | 54 |
| Support Services |  |  |  |
| Finance & Property Services | 221 | 333 | (112) |
| Corporate Management | 541 | 542 | (1) |
| People and Policy | 144 | 137 | 7 |
| Non-Distributed Costs | (421) | (508) | 87 |
| (Variance in brackets denotes an overspend) | 1,617 | 1,582 | 34 |

| Key variances |  |
| --- | --- |
| Legal Salaries | 32 |
| Various Democratic Services budgets | 18 |
| Election expenses | 4 |
| Cash receipting upgrade | (16) |
| Salary savings | 12 |
| Misc overspend | (11) |
| NNDR & Water rates | (30) |
| Rents: Futures Park & Industrial units | (35) |
| insurances | (25) |
| H' & Safety reports | (7) |
| Miscellaneous saving P&P | 7 |
| Pension costs | (9) |
| Misc Insurances | 13 |
| Car loans - budget error | (11) |
| Interest on bank investment | 92 |
|  | 34 |

Section 2 – Performance against the Council’s Priorities

Section 3 – Implementing the Council’s Corporate Plan

This section of the report provides a detailed performance up-date against each of the actions in the Council’s Corporate Plan which are due for completion by March 2009.

Guide for Actions Report

The Theme heading displays the corporate priority grouping for the following batch of Indicators

Theme: Priority *

| Action Code | Action Title | Due Date | Responsible Officer | Start Date | Completed Date | Latest Note | Latest Date | RAG Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Risk/RAG (Red Amber Green) Status |  |
| --- | --- |
|  | Project on track, no substantial issues or risks which require action from the Council’s Programme Board |
|  | Some issues or risks which require action from the Council’s Programme Board to keep the project on track |
|  | Project in jeopardy – serious issues or risks needing urgent action |

| Quarter 2 Action Report 2008-9 Report Author: Lee Admin_Birkett Report Type: Action Report Generated on: 23 October 2008 |  |
| --- | --- |

Theme: Priority 1 - Delivering quality services to our customers

| Action Code | Action Title | Due Date | Responsible Officer | Start Date | Completed Date | Latest Note | Latest Date | RAG Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.01 - P&OD | Achieve Level 3 of the Equality Standard through external accreditation process | 31/03/2009 | Head of People and Policy | 08/10/2008 |  | Currently exploring options in relation to external assessment | 08/10/2008 |  |
| 1.02 - P&OD | Achieve Level 3 of the Equality Standard through external accreditation process- | 31/03/2009 | Head of People and Policy | 08/10/2008 |  | Equality Standard been revised looking to develop own external assessment process | 20/10/2008 |  |
| 1.02.2 - N&SS | Develop and implement "Pride in Rossendale" | 31/03/2009 | Area Manager West | 06/10/2008 |  | Neighbourhood teams now in place and beginning to make contact with Community and Friends groups in relation to Parks and open spaces. | 13/10/2008 |  |
| 1.07 - CS&ICT | Improve Quality of Benefits Services | 30/03/2009 | Service Assurance Manager | 06/10/2008 |  | Annual performance targets have been agreed to deliver continuous service improvement. Local targets are regularly reviewed and Rossendale benchmarks performance with neighbouring LAs to ensure that a high quality service is maintained. Rossendale has introduced a Take Up Strategy and this is supported by an action plan which targets different sectors in our community by customer profiling. Robust working procedures are in place to improve processing times whilst maintaining accuracy. A proactive program of work has been established to identify claims which require review. The majority of Housing Benefit payments are now paid by BACS and this has achieved speed and efficiency. A new project plan is now underway for the implementation of the E Benefits application. E Benefits will provide a much more customer focused service delivery. It will improve processing times and increase customer satisfaction. | 20/08/2008 |  |
| 1.07.2 - CS&ICT | Promote Benefits Take up | 30/03/2009 | Service Assurance Manager | 06/10/2008 |  | Customer profiling information has been used to identify all customers, in Rossendale over 60, not currently claiming HB/CTB but who may qualify. A random sample of these cases has been selected and these customers will be written to/visited. Various other activities are taking place on a month by month basis to actively promote the take up of all benefits. A three month trial has just started to identify customers 60+ who have not provided enough information in order to process their HB/CTB. These customers’ claims will be made ineligible. They are to be visited in order to obtain the info and so process the claim, which may lead to an entitlement to HB/CTB. | 30/07/2008 |  |
| 1.08 - CS&ICT | Improve Quality of Revenues Services | 01/03/2009 | Service Assurance Manager | 16/10/2008 |  | 01-11-2008 Introducing a paperless direct debit instruction. | 21/08/2008 |  |
| 1.14 - Cs | Oversee the delivery of key Partnership events | 15/11/2008 | Communities Manager | 06/10/2008 |  | Ongoing work with Rossendale Leisure Trust and various community groups. Rossendale Alive festival held in the summer which was well delivered by RLT. Currently providing support to the Haslingden Street Fair due to take place in September 08. Overall good progress being made in the delivery of key partnership events. | 19/08/2008 |  |

Theme: Priority 2 - Delivering regeneration across the Borough

| Action Code | Action Title | Due Date | Responsible Officer | Start Date | Completed Date | Latest Note | Latest Date | RAG Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.01 - P&P | Implement the Apprenticeship Policy to recruit apprentices | 09/10/2008 | Head of People and Policy | 09/10/2008 |  | Apprenticeship Policy updated | 18/08/2008 |  |
| 2.02 - P&P | Make a skills pledge and commit to skills for life | 30/10/2008 | Head of People and Policy | 08/10/2008 |  | Signed skills pledge August 2008. | 21/08/2008 |  |
| 2.03 - P&P | Promote the Council as an employer of choice | 30/03/2009 | Head of People and Policy | 08/10/2008 | 20/10/2008 | Attended Burnley Jobs Promotion to promote jobs opportunities within the BME Community. | 18/08/2008 |  |
| 2.01 - N&SS | Deliver local regeneration project | 31/03/2009 | Area Manager West; Environmental Health Manager | 10/09/2008 |  | Please see sub actions 2.01.1 and 2.01.2 | 21/08/2008 |  |
| 2.01.1 - N&SS | Implement enforcement powers to stimulate regeneration | 31/03/2009 | Area Manager West | 10/09/2008 |  | Work continuing in this area continued use of sec 215 Town and Country Planning Act Case numbers now up 160 with 65 active cases | 16/10/2008 |  |
| 2.01.2 - N&SS | Develop and deliver a programme of environmental enhancements within Elevate programme | 31/03/2009 | Environmental Health Manager | 16/10/2008 |  | Project within the Elevate Programme on going successful projects include the view, Bankside Lane and spring Terrace. Several other projects to be initiated. | 16/10/2008 |  |
| 2.03 - Rg | Development of enhanced programme management within the Regeneration Service | 28/02/2009 | Administration Assistant - Regeneration; Head of Regeneration | 08/09/2008 |  | Cabinet approved the proposed management arrangements. A programme delivery manager is now in post. | 06/10/2008 |  |
| 2.05.1 - Rg | Put in place Programme leader, programme manager and project leads for each project within the programme | 31/03/2009 | Administration Assistant - Regeneration; Head of Regeneration | 08/09/2008 |  | Programme leader, Steve Jackson and programme manager Fraser Nash are now in place as are project leads for each of the projects within the programme. | 06/10/2008 |  |
| 2.08.1 - Rg | Monitor the tourism contract being delivered by Brighter Business Solutions | 31/03/2009 | Administration Assistant - Regeneration; Head of Regeneration |  |  | The monitoring of the tourism contract is continuing with a tourism action plan being adopted by the tourism steering group and a database of tourism businesses being established. | 01/10/2008 |  |
| 2.08.2 - Rg | Prepare a tourism strategy for the Council and review the tourism contract | 31/12/2008 | Administration Assistant - Regeneration; Head of Regeneration |  |  | The tourism strategy will be prepared once the staff are in place and a decision on the tourism contract will be made later in the year. | 01/10/2008 |  |

Theme: Priority 3 - Keeping our Borough clean and green

| Action Code | Action Title | Due Date | Responsible Officer | Start Date | Completed Date | Latest Note | Latest Date | RAG Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.02.4 - N&SS | Ensuring our town centres, gateways and corridors are clean and well maintained | 31/03/2009 | Area Manager West | 08/09/2008 |  | Work continues to develop in this area there is a Members Task and Finish group on grass cutting in an effort to achieve a co-ordinated approach. Further work to be done by both Rossendale and Lancashire C.c. | 16/10/2008 |  |
| 3.04 - N&SS | Delivering appropriate Waste Management Infrastructure | 31/03/2009 | Deputy Chief Executive; Operations Manager | 08/09/2008 |  | Options appraisal and feasibility study now completed and now linked to Rossendale waste management strategy. Upgrades to existing waste management facilities phase 1 also completed. Phase 2 improvements linked to Rossendale waste management strategy currently Jason Foster and Keith Jenkins undertaking COTC training for waste management licence with an anticipated completion dates as 31/03/2009. Rosendale waste management strategy currently being reviewed with a view to implementing an appropriate infrastructure to ensure cost effective integrations with Lancashire’s PFI. | 16/10/2008 |  |

Theme: Priority 4 - Promoting Rossendale as a cracking place to live and visit

| Action Code | Action Title | Due Date | Responsible Officer | Start Date | Completed Date | Latest Note | Latest Date | RAG Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.01 - P&P | Maintain Corporate Publications Programme | 01/03/2009 | Communications Manager | 08/10/2008 |  | Rossendale Alive is currently being graphic designed and will be send for printing shortly. Grapevine was circulated in early September and work on the next edition will begin in November. The Corporate Plan has been published. | 16/10/2008 |  |
| 4.02 - P&P | Deliver effective promotion of specific campaigns and activities | 01/03/2009 | Communications Manager | 08/10/2008 |  | Rossendale Pride - Further promotional work has taken place with information on the website, an article in Rossendale Alive and details provided in Team Briefing. Local Democracy Week has proved to be a big success with very positive feedback provided from local schools. Articles on the new Communities Team and the Health Hub in Rawtenstall is featured in the Autumn Rossendale Alive newsletter. | 16/10/2008 |  |
| 4.02.4 - P&P | Support and advise the NHS in relation to communication issues around the proposed Rossendale Health Campus and ongoing health campaigns | 01/03/2009 | Communications Manager | 08/10/2008 |  | Communications Manager attending the PCT Community Engagement Team for the new Health Centre and feeding in suggestions to the Project Manager. The next meeting of the group in November will focus on Communications Activity. | 17/10/2008 |  |

Theme: Priority 5 - Improving health and well-being across the Borough

| Action Code | Action Title | Due Date | Responsible Officer | Start Date | Completed Date | Latest Note | Latest Date | RAG Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5.01 - P&P | Develop a Strategy which promotes Health and Well Being within the workforce and offers a range of activities which will improve health and well being | 01/01/2009 | Head of People and Policy; HR Manager | 08/10/2008 |  | Strategy drafted considered by O&S and JCC. Smoking cessation and blood pressure checks implemented | 21/08/2008 |  |

Theme: Priority 6 - A well managed council

| Action Code | Action Title | Due Date | Responsible Officer | Start Date | Completed Date | Latest Note | Latest Date | RAG Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 6.02 - F&P | Extracting Costs | 28/02/2009 | Head of Finance and Property |  |  | Preparation for 09/10 now commenced with first draft scheduled for Sept 09. Members will commence to match resources and priorities during Oct - Dec 2009. | 20/08/2008 |  |
| 6.09.2 - P&P | Implementation of the change | 01/01/2009 | Head of People and Policy |  |  | No decision made in relation to accommodation so no action required at this stage | 22/10/2008 |  |

Section 4 – Performance Indicators

Detailed performance information relating to the achievement of targets against performance indicators

| Legend |  |
| --- | --- |
|  | On/above Target |
|  | Marginally Below Target |
|  | Below Target |
|  | Unknown |

Corporate View of Performance Indicators – Quarter 2

Guide for Performance Indicator Report

The Theme heading displays the corporate priority grouping for the following batch of Indicators

Gauge Aim

This indicates whether the aim of the gauge is to have a high or a low number as possible

Value & Target

These figures show the actual performance value and the target performance value

Theme: Priority *

|  |  |  | Quarter 2 2007-8 |  |  | Quarter 2 2008-9 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PI Code | Short Name | Responsible Officers | Q2 2007/08 |  |  | Q2 2008/09 |  |  |  |  | Annual 2008/09 | Gauge Aim | Expected Outcome |
|  |  |  | Value | Target | Status | Value | Target | Status | Long Trend | Note |  |  |  |
| LI *** |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NI *** |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NI *** LAA |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Status |  |
| --- | --- |
|  | This PI is significantly below target. |
|  | This PI is slightly below target. |
|  | This PI is on target. |
|  | This PI cannot be calculated. |
|  | This PI is a data-only PI. |

| Long Trend |  |
| --- | --- |
|  | The value of this PI has improved in the short term. |
|  | The value of this PI has worsened in the short term. |
|  | The value of this PI has not changed in the short term. |
|  | This Trend cannot be calculated. |

PI Code

LI – Local Indicators

LI 1-249 – Local Indicators which are ex BVPIs

NI – National Indicators

NI *** LAA – NIs which are part of the Local Area Agreement

| Quarter 2 Performance Indicator Report 2008-9 Notes There is no historic data for most National Indicators (NIs) as 2008-9 is the first year of collection. Report Author: Lee Admin_Birkett Report Type: PI Report Generated on: 21 October 2008 |  |
| --- | --- |

Rows are sorted by PI Code.

Theme: Priority 1 - Delivering quality services to our customers

|  |  |  | Quarter 2 2007-8 |  |  | Quarter 2 2008-9 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PI Code | Short Name | Responsible Officers | Q2 2007/08 |  |  | Q2 2008/09 |  |  |  |  | Annual 2008/09 | Gauge Aim | Expected Outcome |
|  |  |  | Value | Target | Status | Value | Target | Status | Long Trend | Note |  |  |  |
| LI 109b | Minor applications determined in 8 weeks | Technical Assistant - Planning | 86.47% | 78.00% |  | 91.04% | 80.00% |  |  | 61 (of 67) minor application determined within the statutory 8 week period. | 80.00% | Aim To Maximise | On Target |
| LI 109c | Planning Applications: 'Other' applications | Technical Assistant - Planning | 95.65% | 80.00% |  | 89.90% | 85.00% |  |  | 89 (of 99) other applications determined within the statutory 8 week period. | 85.00% | Aim To Maximise | On Target |
| LI 78a | Speed of processing - new HB/CTB claims (LI 9) | Service Assurance Manager | 23.5 | 29.7 |  | 19.4 | 20.0 |  |  | Performance has exceeded target this quarter and it is expected that this trend will continue | 20.0 | Aim To Minimise | Exceeding Target |
| NI 180 | The number of changes of circumstances which affect customers’ HB/CTB entitlement within the year. | Service Assurance Manager |  |  |  | 2791 | 2719 |  |  | This figure represents performance between June 08 and 2nd September 08. Information prior to this is not available from the DWP. | 5438 | Aim To Maximise | On Target |
| NI 181 | Time taken to process Housing Benefit/Council Tax Benefit new claims and change events | Service Assurance Manager |  |  |  | 15.3 | 17.0 |  |  | Due to data protection restrictions on transfer of information to the department for work and pensions no results have been returned from the DWP. However internal records have been used to estimate performance to date. | 17.0 | Aim To Minimise | On Target |

Theme: Priority 2 - Delivering regeneration across the Borough

|  |  |  | Quarter 2 2007-8 |  |  | Quarter 2 2008-9 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PI Code | Short Name | Responsible Officers | Q2 2007/08 |  |  | Q2 2008/09 |  |  |  |  | Annual 2008/09 | Gauge Aim | Expected Outcome |
|  |  |  | Value | Target | Status | Value | Target | Status | Long Trend | Note |  |  |  |
| LI 109a | Major applications determined in 13 weeks | Technical Assistant - Planning | 50.00% | 60.00% |  | 100.00% | 65.00% |  |  | 1 Major Application determined within the statutory period of 13 weeks | 65.00% | Aim To Maximise | On Target |
| LI 183b | Length of stay in temporary accommodation -Hostel (weeks) | Strategic Housing and Partnerships Manager | 0.00 | 3.00 |  | 0.00 | 2.00 |  |  | At the end of September there were no cases in temporary accommodation | 2.00 | Aim To Minimise | Marginally Below Target |
| LI 213 | (LAAH16) Housing Advice Service: preventing homelessness | Strategic Housing and Partnerships Manager | 1.2 | 0.5 |  | 1.5 | 1.0 |  |  | There were 8 cases which were prevented from becoming homeless in the second quarter | 2.0 | Aim To Maximise | Exceeding Target |
| LI 64 | (LAAH20) No of private sector vacant dwellings that are returned into occupation or demolished | Administration Assistant - Regeneration; Strategic Housing and Partnerships Manager | 22.00 | 20.00 |  | 0.00 | 18.75 |  |  | Cabinet approved CPO of 2 long term vacant properties on Blackburn Road Haslingden. Performance against this target remains low. Exploring ways to build capacity to achieve the target. | 45.00 | Aim To Maximise |  |

Theme: Priority 3 - Keeping our Borough clean and green

|  |  |  | Quarter 2 2007-8 |  |  | Quarter 2 2008-9 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PI Code | Short Name | Responsible Officers | Q2 2007/08 |  |  | Q2 2008/09 |  |  |  |  | Annual 2008/09 | Gauge Aim | Expected Outcome |
|  |  |  | Value | Target | Status | Value | Target | Status | Long Trend | Note |  |  |  |
| LI 218a | Abandoned vehicles - % investigated within 24 hrs | Area Manager West | 100.00% | 98.00% |  | 100.00% | 98.00% |  |  | Second quarter number of requests for service continue to fall fewer vehicles removed, New legislation combined with better enforcement measures have contributed to decline in abandoned vehicles downward trend continues | 98.00% | Aim To Maximise | Exceeding Target |
| LI 218b | Abandoned Vehicles - % removed within 24 hours of required time | Area Manager West | 100.00% | 98.00% |  | 100.00% | 100.00% |  |  | Second quarter number of requests for service continue to fall fewer vehicles removed, New legislation combined with better enforcement measures have contributed to decline in abandoned vehicles downward trend continues | 100.00% | Aim To Maximise | Exceeding Target |
| LI 82ai | % of Household Waste Recycled | Business Support Manager | 24.78% | 24.50% |  | 26.90% | 26.50% |  |  | We have increased our figures due to the implementation of the non side waste policy from stickers issued directly onto bins and a mail shot sent to all residents in Rossendale | 26.50% | Aim To Maximise | On Target |
| LI 82aii | Tonnes of Household Waste Recycled | Business Support Manager | 1565.26 | 1475.06 |  | 1692.30 | 1575.21 |  |  | We have increased our figures due to the implementation of the non side waste policy from stickers issued directly onto bins and a mail shot sent to all residents in Rossendale. | 6300.84 | Aim To Maximise | On Target |
| LI 82bi | (CP3.2.2) % of Household Waste Composted | Business Support Manager | 10.14% | 6.20% |  | 12.44% | 7.50% |  |  | We have increased our organic recycling. This will be partly down to the increased number of brown bins allocated to householders | 7.50% | Aim To Maximise | On Target |
| NI 191 | Residual household waste per household | Business Support Manager |  |  |  | 125 | 128 |  |  | Currently on target, confident that yearly target of 510 will be achieved because of the reduced in organic waste during the Winter period. | 510 | Aim To Minimise |  |
| NI 192 LAA | Percentage of household waste sent for reuse, recycling and composting | Business Support Manager |  |  |  | 39.33% | 33.00% |  |  | Currently exceeding target comfortably because of seasonal trends. | 33.00% | Aim To Maximise |  |

Theme: Priority 4 - Promoting Rossendale as a cracking place to live and visit

|  |  |  | Quarter 2 2007-8 |  |  | Quarter 2 2008-9 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PI Code | Short Name | Responsible Officers | Q2 2007/08 |  |  | Q2 2008/09 |  |  |  |  | Annual 2008/09 | Gauge Aim | Expected Outcome |
|  |  |  | Value | Target | Status | Value | Target | Status | Long Trend | Note |  |  |  |
| NI 156 LAA | Number of households living in temporary accommodation | Administration Assistant - Regeneration; Strategic Housing and Partnerships Manager |  |  |  | 0 | 0 |  |  | At the end of September there were no cases in temporary accommodation | 0 | Aim To Minimise |  |

Theme: Priority 5 - Improving health and well-being across the Borough

|  |  |  | Quarter 2 2007-8 |  |  | Quarter 2 2008-9 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PI Code | Short Name | Responsible Officers | Q2 2007/08 |  |  | Q2 2008/09 |  |  |  |  | Annual 2008/09 | Gauge Aim | Expected Outcome |
|  |  |  | Value | Target | Status | Value | Target | Status | Long Trend | Note |  |  |  |
| LI 156 | Buildings Accessible to People with a Disability | Electrical Engineer | 92.00% | 98.00% |  | 79.00% | 99.00% |  |  |  | 99.00% | Aim To Maximise | On Target |
| NI 16 LAA | Serious acquisitive crime rate PSA 23 | Community Safety Manager |  |  |  | 188 | 215 |  |  | The second quarter has again remained well within the target. It is difficult to compare to the same period last year as the indicator has changed from last year, however, certain categories within the indicator such as vehicle crime and burglary are both showing reductions which is contributing to the achievement | 862 | Aim To Minimise |  |
| NI 20 LAA | Assault with injury crime rate | Community Safety Manager |  |  |  | 80 | 135 |  |  | We are unable to compare this figure as this is a new indicator. However there has been a 21% reduction compared to the first quarter | 540 | Aim To Minimise |  |

Theme: Priority 6 - A well managed council

|  |  |  | Quarter 2 2007-8 |  |  | Quarter 2 2008-9 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PI Code | Short Name | Responsible Officers | Q2 2007/08 |  |  | Q2 2008/09 |  |  |  |  | Annual 2008/09 | Gauge Aim | Expected Outcome |
|  |  |  | Value | Target | Status | Value | Target | Status | Long Trend | Note |  |  |  |
| LI 10 | Percentage of Non-domestic Rates Collected | Service Assurance Team | 62.20% | 63.89% |  | 59.61% | 47.66% |  |  | Robust recovery procedures ensure that despite the extra collectable debt due to the increase in empty business rates the section is still ahead of target for the year. | 97.50% | Aim To Maximise | On Target |
| LI 12 | (CP6.3.2) Working Days Lost Due to Sickness Absence (days) | HR Manager | 4.53 | 4.00 |  | 2.72 | 4.25 |  |  | The Sickness Absence Management Procedure has continued to be implemented effectively to ensure support is provided by managers and HR to encourage return to work. | 8.50 | Aim To Minimise | On Target |
| LI 76b | Housing Benefits Security number of fraud investigators | Capita; Service Assurance Team |  |  |  | 2.00 | 2.00 |  |  | The Fraud Section is fully staffed | 2.00 | Aim To Maximise |  |
| LI 79bi | Percentage of Recoverable Overpayments Recovered (HB) that are recovered during period (LI 10) | Service Assurance Manager | 82.79% | 75.00% |  | 85.30% | 90.00% |  |  | Following the changes in computer reporting, £54K has been created and £46K was recovered within this quarter. This equates to an outturn of 85.30%, but work is ongoing to justify these figures as the total outstanding fluctuates significantly. | 90.00% | Aim To Maximise | On Target |
| LI 79bii | HB overpayments recovered as % of the total amount of HB overpayment debt outstanding (LI 11) | Capita; Service Assurance Manager | 15.20% | 14.25% |  | 15.36% | 15.00% |  |  | This outturn is based on the latest figures produced on the Northgate Software. Continued efforts are being made to prove the outstanding debt plus new debt created is accurate (£302,075.84) and that £46,410.93 was recovered during this quarter. | 60.00% | Aim To Maximise | On Target |
| LI 8 | % of invoices paid on time | Finance Manager | 95.87% | 95.00% |  | 94.16% | 97.50% |  |  | Performance dipped in the first quarter of the year, but has been improving steadily since May. Departments have been reminded of the need to use the electronic ordering system for all purchases so that the processing of invoices can as smooth and quick as possible. | 97.50% | Aim To Maximise | Exceeding Target |

Performance Indicator Action Plan – 2008/9

The Council is committed to developing a ‘performance culture’ through embedding a Performance Management Framework that is robust, transparent and accountable. An important part of this process is taking timely, corrective action to improve performance against an indicator that is not achieving the target level of performance as set out within the relevant Business Plan.

This template should be filled in at the end of each quarter for every indicator (or grouping of indicators that belong together e.g. 76 a, b, c & d) not achieving target levels of performance.  The template should be attached against the indicator in Covalent and updated for each quarter that the indicator remains under target.  The completed template will also be appended to the Quarterly Performance Reports produced for Management Team and Members.

| Service Area: |  | Regeneration |  |  |  |  |  |  |  |  |  |  | Lead Officer for P.I. |  |  |  |  | Steve Jackson |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Indicator name & number/s: |  | LI 64 (LAAH20) No of private sector vacant dwellings that are returned into occupation or demolished |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Target achieved in 2007/8? |  | Yes  | No |  |  | Quartile position in 2008/9? |  |  |  | Top | 2nd |  |  | 3rd |  |  | Bottom |  | N/A  |  | Is it a KSI? |  | YES |  | NO  | Is a CPA P.I. ? |  |  | YES |  | NO  |
| PERFORMANCE DURING 2008-9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Quarter 1 |  |  |  | Quarter 2 |  |  |  | Quarter 3 |  |  |  |  |  |  | Quarter 4 |  |  |  |  |  |  | Targeted Quartile Position? |  |  |  |  |  |  |  |  |  |
| Actual | Target |  |  |  | Actual |  | Target |  | Actual |  |  | Target |  |  |  | Actual |  |  |  | Target |  | Top |  | 2nd |  |  | 3rd | Bottom |  | N/A |  |
| 0 | 11.25 |  |  |  | 0 |  | 18.75 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- Please give an objective assessment as to whether the end of year target will be met?

It is unlikely that this target will be met by the end of the year.

- Please explain the reasons why the indicator is not achieving the targeted level of performance:

The main reason for the target not being met is due to capacity issues within the team.  A new structure is being implemented and 3 properties are being taken through the CPO process.

- Please give details of any corrective actions that are currently  being taken and an estimate of the likely impact:

A new structure is being implemented which should be in place by December 08.

- Any action planned in next financial year that will improve performance?

The 09/10 target will seek to redress the under achievement during 08/09 and a firm target will be agreed as part of the business planning process.

Performance Indicator Action Plan – 2008/9

The Council is committed to developing a ‘performance culture’ through embedding a Performance Management Framework that is robust, transparent and accountable. An important part of this process is taking timely, corrective action to improve performance against an indicator that is not achieving the target level of performance as set out within the relevant Business Plan.

This template should be filled in at the end of each quarter for every indicator (or grouping of indicators that belong together e.g.  76 a,b,c & d) not achieving target levels of performance.  The template should be attached against the indicator in Covalent and updated for each quarter that the indicator remains under target.  The completed template will also be appended to the Quarterly Performance Reports produced for Management Team and Members.

| Service Area: |  | Property |  |  |  |  |  |  |  |  |  |  | Lead Officer for P.I. |  |  |  |  | Lee Childs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Indicator name & number/s: |  | LI 156 Buildings Accessible to People with a Disability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Target achieved in 2007/8? |  | Yes | No  |  |  | Quartile position in 2007/8? |  |  |  | Top | 2nd |  |  | 3rd |  |  | Bottom |  | N/A  |  | Is it a KSI? |  | YES |  | NO  | Is a CPA P.I. ? |  |  | YES |  | NO  |
| PERFORMANCE DURING 2008/9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Quarter 1 |  |  |  | Quarter 2 |  |  |  | Quarter 3 |  |  |  |  |  |  | Quarter 4 |  |  |  |  |  |  | Targeted Quartile Position? |  |  |  |  |  |  |  |  |  |
| Actual | Target |  |  |  | Actual |  | Target |  | Actual |  |  | Target |  |  |  | Actual |  |  |  | Target |  | Top |  | 2nd |  |  | 3rd | Bottom |  | N/A |  |
| 79% | 99% |  |  |  | 79% |  | 99% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

- Please give an objective assessment as to whether the end of year target will be met?

Rossendale Borough Council is now 79% compliant for DDA in public areas within buildings

A further 17% (Rawtenstall Market, Whitworth Pool) will be made compliant this summer (2008 /09) within the capital repairs contract, making a total of 96%.

- Please explain the reasons why the indicator is not achieving the targeted level of performance:

The remaining 4% is at Marl Pitts Pavilion; this has not been included in the 2008 / 09 capital repairs contract because of possible re-development of the site.

- Please give details of any corrective actions that are currently  being taken and an estimate of the likely impact:

N/A

- Any action planned in next financial year that will improve performance?

If re-development of Marl Pitts Pavilion does not go ahead the DDA works will be included in future contract.

Section 5 – Risks

Detailed performance information about the actions being taken to minimise the occurrence of risk

Guide for Risks Report

This heading displays the Category Description and Strategy grouping for the following batch of Indicators

Category Description: 1. Delivering Quality Services to our Customers Strategy: Business

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

|  | Risk Status |  |  |  |
| --- | --- | --- | --- | --- |
|  | The codes in these boxes refer to the Original, Current and Target Impact and Likelihood of a risk in accordance with the Council’s Risk Matrix |  | OK |  |
|  |  |  | Warning |  |
|  |  |  | Alert |  |
| Quarter 2 Risks Report 2008-9 Report Author: Lee Admin_Birkett Report Type: Risk Report Generated on: 31 October 2008 |  |  |  |  |

Category Description: 1. Delivering Quality Services to our Customers Strategy: Business

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1.10 - Rg | New location cannot be found for Rossendale Transport Limited's bus depot | Head of Regeneration | 2 | B | 2 | D | 1 | F |  | there are planning issues relating to the delivery of this project but work continues with partners to achieve a solution | 06/10/2008 |  |

Category Description: 1. Delivering Quality Services to our Customers Strategy: Financial

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1.01 - CS&ICT | Failure to submit LLPG updates to the National Hub | Head of Customer Services | 1 | D | 1 | F | 1 | F | 28/07/2008 | Rossendale have set up an emergency process to deal with any incidents of not being able to send the DTF 7.3. A copy of all the dtf files that are submitted to the hub are backed up onto the storage area network, exchange and the local computer as well. If Rossendale was unable to submit the update a copy of the previous file would be sent to ensure compliance with the MSA is met. | 28/07/2008 |  |

Category Description: 1. Delivering Quality Services to our Customers Strategy: Legal; Regulatory

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1.01 - Le | Provision of timely and effective support and advice to Officers | Executive Director for Business | 4 | D | 3 | E | 2 | E |  | we continue to provide timely and effective advice and systems are being embedded to ensure we can performance manage response times | 24/10/2008 |  |
| R1.02 - Le | Provision of timely and effective support and advice to Elected Members | Executive Director for Business | 2 | D | 3 | C | 2 | E |  | We are reviewing our member enquiry system and setting up new procedures for response times and more effective performance management. Report to EMT will be presented in Oct with an improvement plan and relaunch proposed | 24/10/2008 |  |
| R1.03 - Le | Practice Manager | Executive Director for Business | 2 | D | 3 | E | 2 | E |  | The recent appointment of the acting assistant head of legal will assist in driving this forward and we are aiming for an action plan to be ready by Dec | 24/10/2008 |  |
| R1.04 - Le | Procurement | Executive Director for Business | 2 | D | 2 | D | 2 | E |  | We are looking at a corporate approach to scanning reports will be presented to EMT - the focus is in planning at the moment. Collaborative procurement work continues contracts are being completed | 24/10/2008 |  |
| R1.05 - Le | Court Work | Executive Director for Business | 2 | D | 2 | E | 2 | E |  | We manage the court work well and bring in extra capacity when needed. We are doing more and its working well with successful results. | 24/10/2008 |  |
| R1.06 - Le | Equalities | Executive Director for Business | 2 | D | 2 | D | 2 | E |  | legal are working with HR on improving our service to take into account he EIA we have carried out | 24/10/2008 |  |
| R1.07 - Li | Street Trading - Risk of legal action if the Council fail to enforce the formal adoption | Licensing Manager |  |  | 3 | D | 4 | F |  | Awaiting meeting with Legal Section. Risk is minimal. Any trading on council land requires permission | 17/10/2008 |  |
| R1.08 - Li | DDA 1995 Accessibility Policy - Decrease in accessible vehicles | Licensing Manager | 3 | D | 3 | D | 4 | F |  | Awaiting new guidelines from government, research is ongoing. Meeting project officer for the physically disabled in December. | 17/10/2008 |  |
| R1.09 - Li | Rossendale Test - Decrease in standards may identify public safety risk | Licensing Manager | 3 | C | 3 | C | 4 | B |  | About to go into consultation with the taxi trade with a view to creating a strategy | 17/10/2008 |  |
| R1.10 - Li | Review of Tariff - Financial restraints on the Taxi Trade | Licensing Manager | 3 | D | 4 | F | 4 | B |  | task completed | 10/10/2008 |  |
| R1.11 - Li | Review of 'mini-bus conversions - financial restraints of the taxi trade / public safety | Licensing Manager | 3 | D | 4 | F | 4 | B |  | Task completed | 10/10/2008 |  |
| R1.12 - Dc | Improving levels of customer care | Executive Director for Business | 3 | D | 2 | C | 4 | E |  | Across the service we have different approaches to customer care , the more front facing services need to completely step back and ask who are customers are and to obtain feedback so we can drive through improvements . Planning is an area of focus. Building control do this very well and report to O and S. Embedding a consistent approach across the directorate by march 2009 is the objective . National indicator 14 is also a big consideration. | 24/10/2008 |  |
| R1.13 - Dc | Improvement in the way we provide the Regulatory Services business | Executive Director for Business | 3 | D | 3 | D | 4 | E |  | Further work is required and improvement plans are being worked on and we will use these as the area to focus on to march 2009 | 24/10/2008 |  |
| R1.14 - Dc | Delivery against the National Indicators | Executive Director for Business |  |  | 3 | E | 4 | E |  | Performance is good in Planning and Environmental health and improving. Clearer performance management systems are helping us to focus on performance | 24/10/2008 |  |
| R1.15 - Dc | Delivery of the Equalities Action Plan | Executive Director for Business | 2 | C | 2 | D | 3 | D |  | Clear tasks have been given to officers by next quarter report I hope to report progress. | 24/10/2008 |  |
| R1.16 - Dc | Delivery of a public forum and developers forum | Executive Director for Business | 4 | F | 4 | F | 4 | F |  | Developer forums have been held on the SHLA and other documents / changes to policies and procedures. A public forum is required on the Planning Service and we will pick this up with consultation on the preferred option core strategy | 24/10/2008 |  |
| R1.17 - Dc | Secure arrangements for conservation advice and arboriculture advice | Executive Director for Business | 2 | C | 2 | D | 3 | D |  | Applications have been submitted to English heritage for posts for conservation officer and we await the result of the application. A lot of progress has been made | 24/10/2008 |  |
| R1.18 - Dc | On line applications increase | Executive Director for Business | 3 | E | 3 | E | 3 | D |  | We continue to perform strongly and are one of the best in lancs on this. | 24/10/2008 |  |
| R1.19 - Dc | Greater attendance by the Team at LSP meetings/LPOS meetings | Executive Director for Business | 3 | F | 3 | F | 4 | F |  | We are ensuring we attend LPOS and will be attending LSP meetings | 24/10/2008 |  |

Category Description: 1. Delivering Quality Services to our Customers Strategy: Operational

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1.20 - DS | Not reviewing procedures for public speaking at Committees | Committee and Member Services Manager | 1 | D | 3 | E | 1 | E |  | A questionnaire will be circulated at public meetings to get feedback on the current procedures to see what improvements need to be made. Members will be asked for ideas on how they would like the procedures to develop. It is proposed to start discussions at the Member Development Working Group and ask how members want to take this forward. | 16/10/2008 |  |

Category Description: 1. Delivering Quality Services to our Customers Strategy: People

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1.07 - Cs | Neighbourhood plans not developed | Communities Manager | 2 | D | 2 | E | 2 | E |  | The Council and their partners are presently reviewing their Neighbourhood arrangements (out for consultation) and part of that process will be the development of Neighbourhood Plans. | 16/10/2008 |  |

Category Description: 1. Delivering Quality Services to our Customers Strategy: Reputational

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1.08 - Cs | Community Cohesion action plan not delivered against | Communities Manager | 2 | C | 2 | D | 2 | E |  | Community Cohesion will be a cross cutting theme of the Neighbourhood Plans which are being developed as part of the review of Neighbourhood Management. The actions from the Elected Member training session will also be integrated into the plans. | 16/10/2008 |  |

Category Description: 1. Delivering Quality Services to our Customers; Quarterly Risks 2008-9 Strategy: Business

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1.09 - Rg | Valley Center Project does not go ahead | Head of Regeneration | 2 | C | 1 | D | 1 | F |  | Ashbourne Properties still committed to the project | 06/10/2008 |  |
| R1.11 - Rg | Lancashire County Council is not able to commit sufficient funding to development of sustainable new Rawtenstall bus interchange | Head of Regeneration | 2 | B | 2 | B | 1 | E |  | There have been recent issues relating to the availability of funding from LCC, but assurances have been made by the Leader of LCC that funding will be available to deliver this project | 06/10/2008 |  |
| R1.12 - Rg | External funding is not forthcoming from Elevate and North West development Agency | Head of Regeneration | 2 | C | 2 | C | 3 | D |  | All of the anticipated funding from Elevate for 2008/2009 is now confirmed and projects are on site. All concept forms will have been submitted to the NWDA by end August 2008 and officers continue to liaise with the NWDA regarding progression. In the meantime work continues in parallel to further develop the projects in anticipation of NWDA approving the submissions onto the next detail application stage. The Chief Executive is to discuss the projects with the CE of North West Development Agency during October to monitor progress. | 06/10/2008 |  |

Category Description: 1. Delivering Quality Services to our Customers; Quarterly Risks 2008-9 Strategy: Financial

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1.04 - Cs | The Council fails to work with its partners to help achieve the targets in the LAA | Communities Manager | 2 | B | 2 | D | 2 | E |  | Council meeting re LAA took place last month; attend by both lead and contributing officers for LAA. ^ Weekly meetings will be arranged and Miladur is currently undertaking mapping exercise of all LAA meeting county wide. | 13/10/2008 |  |

Category Description: 1. Delivering Quality Services to our Customers; Quarterly Risks 2008-9 Strategy: People

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1.03 - Cs | The Council fails to provide adequate resources in leading the development of partnership working across the LSP | Communities Manager | 2 | D | 2 | E | 2 | E |  | No update on last months report. The risk remains Very Low | 16/10/2008 |  |
| R1.05 - Cs | The new Place survey is not delivered to government requirements | Communities Manager | 1 | E | 2 | E | 1 | E |  | Survey has been posted out to 3200 households. MORI are managing and administering the process. Good progress being made | 13/10/2008 |  |
| R1.06 - Cs | Staff & partners do not engage with Community Involvement and Engagement Strategy | Communities Manager | 2 | C | 2 | D | 1 | E |  | No update on last months report. The risk remains Very Low | 16/10/2008 |  |

Category Description: 1. Delivering Quality Services to our Customers; Quarterly Risks 2008-9 Strategy: Reputational

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1.02 - CS&ICT | Failure to implement customer service standards | Service Assurance Manager | 4 | C | 3 | E | 4 | F |  | Customer service standards are monitored; any breaches are reported to the respective Heads of Service for resolution. | 21/08/2008 |  |

Category Description: 2. Delivering Regeneration across the Borough Strategy: Legal; Regulatory

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R2.03 - Dc | Approach to S215 Notices and S79 Building Act notices agreed to ensure "place shaping role fully utilised" | Executive Director for Business | 4 | E | 4 | E | 4 | F |  | Meetings have taken place and clear process is being worked on / protocol to work to | 24/10/2008 |  |
| R2.04 - FP | Core Strategy Preferred Option consultation (re) and submission | Principal Planner Forward Planning | 2 | C | 2 | C | 3 | E |  | The Section is on target in preparing the Core Strategy. In July this year the Town and Country Planning (Local Development) (England) (Amendment) Regulations 2008 amended the statutory process in terms of delivering the Local Development Framework, however, this should not prevent the Core Strategy from being adopted in 2010 as intended, although the stages identified in the current Local Development Scheme will have to be amended to take account of the new Regulations. | 31/10/2008 |  |
| R2.07 - FP | Review of Interim Housing Policy | Principal Planner Forward Planning | 4 | E | 4 | E | 4 | F |  | Interim Housing Policy was adopted by Cabinet 30th July 2008. This is therefore no longer a risk. | 16/10/2008 |  |

Category Description: 2. Delivering Regeneration across the Borough; Quarterly Risks 2008-9 Strategy: Legal; Regulatory

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R2.01 - Dc | Issuing of the Valley Centre planning application | Executive Director for Business | 3 | E | 3 | E | 4 | F |  | Section 106 being Negotiated. | 20/08/2008 |  |
| R2.02 - Dc | Processing of other MAA planning applications/health campus application/adrenalin gateway | Executive Director for Business | 3 | E | 3 | E | 4 | F |  | Health Centre campus received. | 20/08/2008 |  |
| R2.05 - FP | Rawtenstall AAP delivery | Principal Planner Forward Planning | 3 | D | 3 | C | 3 | E |  | As 20/08/08. No change. | 16/10/2008 |  |
| R2.06 - FP | Bacup AAP | Principal Planner Forward Planning | 3 | D | 3 | C | 3 | E |  | As 20/08/08. No change. | 16/10/2008 |  |

Category Description: 3. Keeping Our Borough Clean and Green Strategy: Legal; Regulatory

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R3.01 - FP | Climate change/Lifetime homes | Principal Planner Forward Planning | 3 | E | 3 | E | 3 | F |  | Climate change and lifetime homes issues are being dealt with in the appropriate planning policy documents | 31/10/2008 |  |

Category Description: 4. Promoting Rossendale as a cracking place to live and visit Strategy: Legal; Regulatory

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R4.01 - FP | Planning Powers are central to the role of place shaper - promotion of sustainable development/low carbon lifestyles and development resilient to climate change | Principal Planner Forward Planning | 2 | E | 2 | E | 2 | F |  | This will be delivered through the Local Development Framework, particularly the Core Strategy, and interim planning policies as required. | 16/10/2008 |  |
| R4.03 - FP | Ensure the delivery of affordable housing | Principal Planner Forward Planning | 2 | C | 2 | D | 3 | E |  | The Interim Housing Policy, adopted by Cabinet on 30/07/08, seeks to secure the delivery of affordable housing through the determination of planning applications. This is being implemented with 38 affordable houses secured as well as a financial contribution, since February 2007. The section will seek to ensure the delivery of additional affordable housing where appropriate. | 16/10/2008 |  |

Category Description: 4. Promoting Rossendale as a cracking place to live and visit; Quarterly Risks 2008-9 Strategy: Legal; Regulatory

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R4.02 - FP | Delivery of the LDF | Principal Planner Forward Planning | 2 | C | 2 | B | 2 | F |  | As 20/08/08. No change. | 16/10/2008 |  |

Category Description: 5. Improving health and well-being across the Borough Strategy: Legal; Regulatory

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R5.01 - BC | Implement Radon Gas precautions into building works in line with guidance from British Geological Survey | Building Control Manager | 4 | E | 4 | E | 4 | F |  | --all new works now incorporate radon gas membranes | 17/10/2008 |  |
| R5.02 - FP | Promotion of Health and Well Being | Principal Planner Forward Planning | 4 | E | 4 | E | 4 | F |  | The Core Strategy in particular will seek to promote health and well-being within the Borough. | 16/10/2008 |  |
| R5.03 - FP | Play and Open Space SPD | Principal Planner Forward Planning | 2 | E | 2 | E | 2 | F |  | This SPD has been adopted, using powers delegated to the Portfolio Holder on 10th October, by Cabinet meeting of 10th September 2008. | 16/10/2008 |  |

Category Description: 5. Improving health and well-being across the Borough Strategy: Operational

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R5.01 - SSN | Failure to Implement improvement plans for Parks and Cemeteries | Business Support Manager | 2 | D | 3 | D | 4 | E |  | Improvements in parks and cemeteries are currently on target, however as the improvements are linked to stakeholder involvements and assistance from external funding opportunities failure to obtain enough match funding to achieve results still remains a risk. | 07/10/2008 |  |

Category Description: 5. Improving health and well-being across the Borough; Quarterly Risks 2008-9 Strategy: Operational

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R5.02 - SSN | Failure to Implement recommendations of Health & Safety Audit | Business Support Manager | 3 | B | 2 | C | 4 | E |  | Currently risk assessments for refuse collection are being undertaken by the Council's health and safety officer. A number of significant recommendations of improvements to the safety of refuse collections, especially vehicle reversing will be debated at senior management level and outcome will be taken to cabinet for approval. Further risk assessments to be undertaken within parks and open spaces and street cleansing. Recommendation from these exercises will also need to be discussed at senior management level. | 07/10/2008 |  |

Category Description: 6. A Well Managed Council Strategy: Financial

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R6.03 - F&P | Accommodation Strategy | Head of Finance and Property | 2 | C | 2 | C | 2 | E |  | No significant change in that Valley Centre re-development is the catalyst to unlocking resources | 30/10/2008 |  |
| R6.01 - BC | Budget overspend | Head of Finance and Property |  |  |  |  | 1 | D |  |  |  |  |
| R6.23 - El | Failure to hold a constituency/district election | Elections Manager | 1 | F | 2 | E | 1 | F |  | Project plans, emergency plans and risk assessments are completed early in the election timetable in order to negate and prepare for serious difficulties arising. | 03/09/2008 |  |

Category Description: 6. A Well Managed Council Strategy: Information

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R6.03 - P&P | NI data is unreliable/inaccurate | Head of People and Policy | 3 | D | 3 | E | 4 | F |  | Recent Data Quality check confirmed. Dta meeting required standards | 24/10/2008 |  |

Category Description: 6. A Well Managed Council Strategy: Legal; Regulatory

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R6.01 - P&P | Litigation | Head of People and Policy | 1 | E | 2 | E | 2 | E |  | Professional Legal Guidance being sought as necessary | 22/10/2008 |  |
| R6.05 - CS&ICT | Litigation | Head of Customer Services | 2 | D | 2 | D | 2 | E |  | All the existing ICT contracts are currently being evaluated to determine there viability, technical capabilities and current commitments. All contracts will have to be reviewed individually during the next year. | 28/07/2008 |  |
| R6.12 - DS | Agendas not being published in accordance with statutory timescales | Committee and Member Services Manager | 1 | E | 2 | F | 1 | E |  | Regular monitoring by the Committee and Member Services Manager takes place. The office white board has deadline dates of reports, agendas and minutes to ensure we are on track with meeting deadlines. Lead-in times are produced for officers so that deadlines are clearly communicated. | 07/10/2008 |  |
| R6.14 - DS | Procedure for dealing with Councillor Call for Actions not developed | Committee and Member Services Manager | 1 | D | 2 | E | 1 | E |  | Awaiting guidance from central government as Councillor Call for Actions not yet in place. | 15/08/2008 |  |
| R6.17 - El | Failure to acquire timely and accurate documentation within statutory timescales i.e. poll cards, postal ballot packs | Elections Manager | 2 | F | 2 | D | 2 | F |  | May 2008 elections were project managed using legislative deadlines and Electoral Commission guidelines. All processes were carried out within statutory timescales. | 02/09/2008 |  |
| R6.18 - El | Failure to comply or act within key legislation | Elections Manager | 2 | E | 2 | E | 2 | E |  | Project plans for elections and annual canvass are organised within electoral legislation and Electoral Commission guidelines to ensure legislation is complied with. | 02/09/2008 |  |
| R6.22 - El | Failure to adequately and appropriately staff the Electoral Service / Election. | Elections Manager | 2 | E | 3 | E | 2 | E |  | A project plan is devised several months prior to each election (with the exception of by-elections) and the number of staff required in the electoral team is incorporated into this plan. Staffing for polling stations and the count is also started three months prior to election day in order that adequate staff are sourced and there is sufficient time for effective training to be given. Standby staff are also recruited in case of emergencies on election day. The Emergency Plan contains details of outside organisations and bodies where senior electoral staff can be recruited. | 03/09/2008 |  |

Category Description: 6. A Well Managed Council Strategy: Legal; Regulatory; Reputational

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R6.02 - P&P | Payroll | Head of People and Policy | 3 | E | 3 | E | 3 | E |  | Continued to be monitored. Contingency Planning in place. | 22/10/2008 |  |

Category Description: 6. A Well Managed Council Strategy: Legal; Reputational

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R6.20 - El | Failure to ensure polling stations are DDA compliant / accessible to all | Elections Manager | 2 | C | 3 | C | 2 | C |  | Polling stations are assessed each year and issues addressed or alternative venues located. It may not always be possible to have all stations DDA compliant as most of the buildings used do not belong to the Council and in many areas do not have other public buildings that can be utilised. | 02/09/2008 |  |

Category Description: 6. A Well Managed Council Strategy: Operational

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R6.01 - CS&ICT | Risk of data centre air conditioning failing | Head of Customer Services | 1 | E | 1 | E | 1 | F | 28/07/2008 | The replacement two 8.1KW air conditioning units have been successfully installed into the Hardmans Mill data centre. Rossendale now have three individual air conditioning units installed at Hardmans Mill, although the support contract at present is still with sungard which represents a risk. | 28/07/2008 |  |
| R6.02 - CS&ICT | Maintenance contracts for air conditioning. | Head of Customer Services | 1 | D | 1 | D | 1 | F | 28/07/2008 | The new air conditioning units have been successfully installed at Hardmans Mill, the contract fore support at present is still with sungard. This is currently under negotiation, Rossendale have sourced a new support provider who lives in the local area. | 28/07/2008 |  |
| R6.02 - BC | Business continuity | Head of Finance and Property | 3 | D | 3 | D | 4 | D |  |  |  |  |
| R6.07 - DS | Joint elected member training plan with the County Council not developed | Committee and Member Services Manager | 3 | E | 3 | E | 3 | F |  | County Councillors have been invited to particular training events. A joint programme of Local Democracy Week events has also been arranged to share learning with young people about Borough and County matters. | 16/10/2008 |  |
| R6.10 - DS | Failure to apply for re-assessment of the North West Charter | Committee and Member Services Manager | 2 | D | 3 | E | 2 | F |  | The Committee and Member Services Manager with North West Employers on 16.10.08 to discuss process. Further meeting to be arranged with Elected Members through the Member Development Working Group. | 16/10/2008 |  |
| R6.11 - DS | The "Know Your Councillor Guide" is not produced | Committee and Member Services Manager | 3 | E | 3 | E | 3 | E |  | The Know Your Councillor Guide will be published in 2008/09. Discussions are taking place with the publisher regarding timescales for publication. | 15/08/2008 |  |
| R6.13 - DS | Staff not clear on decision making processes of the Council | Committee and Member Services Manager |  |  | 2 | E | 1 | E |  | Democratic Services are available to give advice to officers on committee processes. | 07/10/2008 |  |
| R6.15 - DS | Failure to implement Civic Protocol | Committee and Member Services Manager | 2 | E | 3 | E | 2 | E |  | A Flag Flying Policy is being developed as part of the Civic Protocol and will be considered by the Member Working Group. A new flag pole has been erected in Rawtenstall and it is proposed to put a notice board next to this to keep members of the public informed. | 16/10/2008 |  |
| R6.16 - El | Failure to safeguard data / key documentation | Elections Manager | 2 | F | 2 | D | 2 | F |  | Electoral data is stored on the Council's main server which is backed up and has systems in place to negate hackers. A limited number of Democratic staff have access to personal data required for elections and they are trained on the legislation surrounding its use. As information held now includes signatures and dates of birth of those persons requiring absent voting all staff are made aware of security and related data protection issues. | 02/09/2008 |  |

Category Description: 6. A Well Managed Council Strategy: People

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R6.19 - El | Failure to ensure the health and safety of staff and the public. | Elections Manager | 2 | E | 2 | E | 2 | E |  | Risk assessments are carried out annually for polling stations, electoral staff and canvassers to reduce risk to staff and the public. These are done using Electoral Commission and Association of Electoral Administrators guidelines and in conjunction with Beacon councils. | 02/09/2008 |  |

Category Description: 6. A Well Managed Council Strategy: Reputational

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R6.02 - F&P | Business Continuity | Finance Manager; Head of Finance and Property | 2 | D | 2 | D | 3 | F |  | ICON upgrade delayed until confirmation of hardware requirements were received. Hardware now ordered and implementation pending. Further testing then required to ensure required home access for banking functions and back-up processes once staff have moved offices and JE has been replaced. Extension of BACS to refunds has decreased reliance on cheques even further. Separate BCP required for new AUDDIS BACS updates once these have been fully implemented. | 21/10/2008 |  |
| R6.08 - DS | Programme of events not delivered during Local Democracy Week | Committee and Member Services Manager | 2 | D | 4 | F | 2 | E |  | Programme of events has been developed. | 07/10/2008 |  |
| R6.21 - El | Failure to safeguard the service/election from fraud and corruption | Elections Manager | 2 | F | 2 | E | 2 | F |  | In order to safeguard the service and elections from fraud and corruption data and paper files are stored securely, forms are checked against information held and joint working is carried out with the Police. Legislation is also strictly adhered to and Electoral Commission guidelines are utilised. | 03/09/2008 |  |

Category Description: 6. A Well Managed Council; Quarterly Risks 2008-9 Strategy: Financial

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R6.01 - F&P | Embedding Financial Management | Head of Finance and Property | 1 | C | 3 | E | 3 | F |  | The Audit Commission has given its initial feedback on UoR 2007. Officers are currently gathering additional evidence to further consolidate the current published score of 2 | 30/10/2008 |  |
| R6.04 - F&P | Asset Disposal Programme | Head of Finance and Property | 2 | D | 2 | D | 3 | E |  | Whitworth NO disposed of during Oct 08 have just achieving its reserve price. Market and climate still against RBC re further disposals. | 30/10/2008 |  |

Category Description: 6. A Well Managed Council; Quarterly Risks 2008-9 Strategy: Financial; Legal; People; Regulatory; Reputational

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R6.24 - El | Failure to organise elections (Local, National, European, etc) | Elections Manager | 2 | B | 2 | F | 4 | F |  | Preparations underway for 2008 Electoral role | 20/08/2008 |  |

Category Description: 6. A Well Managed Council; Quarterly Risks 2008-9 Strategy: Operational

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R6.03 - CS&ICT | Contractual difficulties with Sungard undermine key improvement processes in all areas of the council. | Head of Customer Services | 1 | B | 1 | B | 1 | F |  | A cabinet report has been produced that contains strategic alternatives. | 16/10/2008 |  |
| R6.04 - CS&ICT | Centralised Back up process | Head of Customer Services | 1 | C | 1 | C | 1 | D | 28/07/2008 | A centralised back up process has been implemented in the Hardmans Mill data centre. At present we are waiting replies back from a few suppliers such as Civica to complete the project. | 28/07/2008 |  |
| R6.06 - CS&ICT | Business Continuity | Head of Customer Services | 1 | C | 1 | C | 1 | D | 28/07/2008 | A detailed Disaster recovery specification has been developed and it will go out to quote, it is anticipated that the contract will be awarded in Mid November 2008. | 16/10/2008 |  |
| R6.09 - DS | Member Development Strategy for 2008/09 not implemented | Committee and Member Services Manager | 1 | E | 3 | E | 1 | F |  | The Strategy is being implemented. Training is held for members. The Member Development Working Group champion training at Group meetings. | 07/10/2008 |  |

Category Description: 6. A Well Managed Council; Quarterly Risks 2008-9 Strategy: Strategic

| Risk Code | Risk Title | Responsible Officer | Original Impact | Original Likelihood | Current Impact | Current Likelihood | Target Impact | Target Likelihood | Target Date | Latest Note | Latest Date | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R6.08 - SSN | Waste Strategy | Business Support Manager | 2 | A | 2 | A | 3 | D |  | Further report on a waste strategy for Rossendale to be created detailing the feasibility of operating a waste transfer station or bulking facility within Rossendale. If a decision can not be reached on a latter a cost analysis will be undertaken on delivering waste and recyclables to a partner waste transfer station, and or a Lancashire County approved facility, this being either Whiney Hill or the proposed facility at Huncoat. | 07/10/2008 |  |

Section 6 – Financial Health Indicators

Section 6 - Financial Health Indicators

The Following table attempts to give some context to the financial performance reported to Members during 2008/09:

- Cash Balances – continue to have been strong over the second quarter of 08/09

- Bank Interest generated – RBC have benefited from rates as high as +6.00% compared to current bank base rate of 4.5%

- Debtor management – steady improvement. New software system ARMS will produce benefits over the remainder of 08/09

- Steady and consistent use of electronic payment methods

- Best procurement practices are being embedded, with benefits from the newly launched Team Lancashire procurement to come into play over the next 12 months as we see a transition from East Lancashire e-Procurement.

|  |  | As at 31 March 2008 | End Q2 2008/09 | Long Term Trend |
| --- | --- | --- | --- | --- |
| 1 | Targeting a score of 3 (by 09/10) in the annual Use of Resources assessment by the Audit Commission | TBC | TBC | Audit Commission have given their initial feedback on the 07/08 score. Officers are gathering further evidence. Final report due Dec ‘08. |
| 2 | Cash & Indebtedness (£000) | £4,058 | £9,532 | Traditionally June is the peak, however available cash increased over the 2nd qtr. Anticipate a reduction over the 2nd half of the year. |
| 3 | Average Debtor Days | 66 | 92 | Compares to 83 as at Sept 07, though Sept’ saw the significant billing of ad hoc S106 invoices. |
| 4 | % Proportion of debtors over 6 months old | 31% | 33% | Still assuming target of 30% |
| 5 | Level of Council Tax arrears (£000) | £2,374 | Annual | Annual calculation |
| 6 | Level of NNDR arrears (£000) | £254 | Annual | Annual calculation |
| 7 | % of payments made by electronic means | 74% | 82% | Steady increase |
| 8 | % Interest earned (above SECTOR model portfolio) | 0.18 | (0.13) | Sector Short Model running at 6.19% (Sept ‘08). RBC averaging 6.06% Sector model is based on their ability to invest for an average 232 days. The RBC maximum invested has been 90days @ 6.2% |
| 9 | Corporate Spend (£000) | £7,074 | £1,383,475 | 24% of programme spent or committed in the 1st half. Pressure on capital receipts due to current financial / economic climate |
| 10 | Corporate Spend placed with local companies (£000) | £948 | £261 | Slight increase from last quarter no new national framework agreements entered into |
| 11 | % of above placed thro' collaborative arrangements | 22.2% | 18.8% | Slight drop as we introduce gateway reviews to the procurement process ensuring the collaborative option is best value for Rossendale |
| 12 | No of invoices | 4,084 | 1171 | Steady / consistent |
| 13 | Average value of invoices | £853 | £1,181 | Similar to Q2 last year slight increase |
| 14 | Average spend per supplier | £3,775 | £5,362 | Steady / consistent |
| 15 | Value of electronic payments (£000) | £58,955 | £1,368,938 | Steady / consistent |
| 16 | % value of electronic payments | 85% | 98.95% | Expect to see above 98% in long term |

| Ref’n |  | Asset 31 March 2008 | End Q1 2008/09 | Long Term Trend |
| --- | --- | --- | --- | --- |
| 1 | Targeting a score of 3 (by 09/10) in the annual Use of Resources assessment by the Audit Commission | TBC | TBC | Audit Commission currently assessing |
| 2 | Cash & Indebtedness (£000) | £4,058 | £8,947 | Reduction over the longer term |
| 3 | Average Debtor Days | 66 | 79 | Compares to 77 as at July 07 |
| 4 | % Proportion of debtors over 6 months old | 31% | 33% | Still assuming target of 30% |
| 5 | Level of Council Tax arrears (£000) | £2,374 | Annual | Annual calculation |
| Ref’n |  | Asset 31 March 2008 | End Q1 2008/09 | Long Term Trend |
| 6 | Level of NNDR arrears (£000) | £254 | Annual | Annual calculation |
| 7 | % of payments made by electronic means | 74% | 82% | Steady increase |
| 8 | % Interest earned (above SECTOR model portfolio) | 0.18 | (0.137) | SECTOR Model running at 5.837% (15/08/09). RBC averaging 5.7% |
| 9 | Corporate Spend (£000) | £3,484 | £1,116 | Steady / consistent |
| 10 | Corporate Spend placed with local companies (£000) | £948 | £222 | Steady / consistent |
| 11 | % of above placed thro' collaborative arrangements | 22.2% | 19.9% | Steady / consistent |
| 12 | No of invoices | 4,084 | 1,272 | Steady / consistent |
| 13 | Average value of invoices | £853 | £875 | Steady / consistent |
| 14 | Average spend per supplier | £3,775 | £3,809 | Steady / consistent |
| 15 | Value of electronic payments (£000) | £58,955 | £11,050 | Steady / consistent |
| 16 | % value of electronic payments | 85% | 98% | Expect to see above 95% in long term |

Section 7 – Complaints

Section 7 – Complaints

The Council has set standards to be achieved when managing the complaints received by the Council & monitors the progress we are making in achieving these standards upon a regular basis. This section of the report provides a summary of the number of complaints received by the Council between July and September 2008 - broken down by the area of service that the complaint related to, and by the nature of the complaint.

| Head of Service | Service Area | Team | Complaints O/S a beginning 1/4 | Complaints Received | Complaints Closed | Complaints O/S at end 1/4 |
| --- | --- | --- | --- | --- | --- | --- |
| Chief Executive | People & Policy | Human Resources |  |  |  |  |
|  |  | Policy & Performance |  |  |  |  |
|  |  | Communications |  |  |  |  |
|  | Finance & Property | Financial Services |  |  |  |  |
|  |  | Property Services |  |  |  |  |
| Place | Street Scene | Refuse |  |  |  |  |
|  |  | Cleansing |  |  |  |  |
|  |  | Parks & Open Spaces |  |  |  |  |
|  | Customer Services | Capita - Council Tax Recovery |  | 2 | 2 |  |
|  |  | Capita- Council Tax |  | 4 | 4 |  |
|  |  | Capita - Call Centre |  |  |  |  |
|  |  | Capita - Benefits |  | 5 | 5 |  |
|  |  | Capita- NNDR |  |  |  |  |
|  |  | Capita - OSS |  |  |  |  |
|  |  | ICT |  |  |  |  |
|  |  | Customer Service |  |  |  |  |
|  | Communities | Community Safety |  |  |  |  |
|  |  | LSP Delivery |  | 1 | 1 |  |
|  |  | Service Development |  |  |  |  |
|  |  | Area Offices |  | 5 | 5 |  |
|  | Regeneration | Regeneration Delivery |  |  |  |  |
|  |  | Regeneration Progs |  |  |  |  |
|  |  | Economic Development |  |  |  |  |
|  |  | Traffic & Parking |  | 1 | 1 |  |
| Business | Legal | Legal Services |  |  |  |  |
|  |  | Committee & Member Services |  |  |  |  |
|  |  | Elections |  |  |  |  |
|  | Building Control | Building Control |  |  |  |  |
|  | Planning | Forward Planning |  |  |  |  |
|  |  | Development Control | 1 | 8 | 9 |  |
|  |  | Land Charges |  |  |  |  |
|  | Environmental Health | Environmental Health |  |  |  |  |
|  |  | Licensing |  |  |  |  |
|  |  | Total | 1 | 26 | 27 | 0 |

7.1   Category of Complaint

|  | Type of Complaint | Number When a complaint is received by the Council it is assigned to one of seven categories, according to the nature of the complaint. In this way we can monitor whether particular themes or issues are emerging. |
| --- | --- | --- |
| 1 | Technical/legal/regulatory issue | 0 |
| 2 | Poor communication | 3 |
| 3 | Delayed response/lack of response | 8 |
| 4 | Complaint against a named officer | 2 |
| 5 | Complaint received via MP | 0 |
| 6 | Complaint received via Councillor | 0 |
| 7 | Complaint about RBC policy or procedures | 13 |
|  | No type of complaint assigned |  |
|  | Total | 26 |

7 .2 - Ombudsman Complaints

If a member of the public feels that the Council has not dealt adequately with their complaint, they may refer their complaint to The Local Government Ombudsman (LGO) who investigates complaints by members of the public who consider that they have been caused injustice through administrative fault by local authorities and certain other bodies. Rossendale Borough Council has no control over the duration of an Ombudsman investigation – they can take days, weeks or even years.

The Council has received recognition from the Ombudsman in relation to its work in improving the management of complaints and how this has resulted in much fewer complaints being made to the Ombudsman. This work has also led to a substantial reduction in the number of ‘open’ complaints being handled by the Ombudsman.

Ombudsman Complaints (1st July 2008 to 30th September 2008)

| Head of Service | Service Area | O/S at start | New | Completed | O/S at end |
| --- | --- | --- | --- | --- | --- |
| Place | Capita – Council Tax | 0 | 1 | 1 | 0 |
|  | Leisure and Culture | 0 | 1 | 1 | 0 |
| Business | Development Control | 1 | 5 | 5 | 1 |
|  | Development Control - Enforcement | 1 | 0 | 0 | 1 |
| Executive | Other – Property Repairs | 0 | 1 | 0 | 1 |
|  | Total | 2 | 8 | 7 | 3 |